KENYA JIKO KISASA IMPROVED COOKSTOVE PROGRAM I

Document Prepared by Guangzhou Iceberg Environmental Consulting Services Co., Ltd.

| Project title | Kenya Jiko Kisasa Improved Cookstove Program I |
| --- | --- |
| Project ID | 3197 |
| Monitoring period | 21/06/2022 to 20/06/2024 |
| Original date of issue | -2024 |
| Most recent date of issue | NA |
| Version | 01 |
| VCS Standard Version | VCS Standard Version 4.4 |
| Prepared by | Guangzhou Iceberg Environmental Consulting Services Co., Ltd. |

Contents

1	Project Details	4

1.1	Summary Description of the Implementation Status of the Project	4

1.2	Audit History	4

1.3	Sectoral Scope and Project Type	5

1.4	Project Proponent	5

1.5	Other Entities Involved in the Project	5

1.6	Project Start Date	5

1.7	Project Crediting Period	5

1.8	Project Location	6

1.9	Title and Reference of Methodology	7

1.10	Double Counting and Participation under Other GHG Programs	7

1.11	Double Claiming, Other Forms of Credit, and Scope 3 Emissions	7

1.12	Sustainable Development Contributions	8

1.13	Commercially Sensitive Information	13

2	Safeguards and Stakeholder Engagement	13

2.1	Stakeholder Engagement and Consultation	13

2.2	Risks to Stakeholders and the Environment	16

2.3	Respect for Human Rights and Equity	17

2.4	Ecosystem Health	18

3	Implementation Status	19

3.1	Implementation Status of the Project Activity	19

3.2	Deviations	19

3.3	Grouped Projects	19

3.4	Baseline Reassessment	19

4	Data and Parameters	19

4.1	Data and Parameters Available at Validation	20

4.2	Data and Parameters Monitored	22

4.3	Monitoring Plan	26

5	Quantification of GHG Emission Reductions and Removals	30

5.1	Baseline Emissions	30

5.2	Project Emissions	30

5.3	Leakage Emissions	30

5.4	GHG Emission Reductions and Carbon Dioxide Removals	30

APPENDIX 1: Statement about outcomes of SDGs	34

Project Details

Summary Description of the Implementation Status of the Project

The project involves distribution of fuel-efficient Jiko Kisasa improved cookstoves (hereinafter referred to as “ICSs”) in the Republic of Kenya. The ICSs disseminated through this project replace the old low efficient baseline cookstoves in rural area of Kenya. The ICSs are produced by local factories.

Through this project, Guangzhou Iceberg Environmental Consulting Services Co., Ltd. (hereinafter referred to as “Iceberg”) plans distribute approximately 100,000 ICSs free of charge to households in rural area of Kenya in 2 years. The start date of the project was 21/06/2022. 26,130 ICSs have been distributed till 20/06/2024, and 25,966 are still operating according to the monitoring survey.

Before the implementation of the project, local people mostly used traditional solid-fuel cooking solutions such as open fire or three-stone fires. They spent plenty of time to collect firewood every day due to low combustion efficiency of baseline cooking devices. The ICS burnt wood more efficiently thereby improving thermal transfer to pots, hence saving firewood. The project has reduced the GHG emission by less non-renewable firewood combustion as well as slowing the rapidly progressing deforestation in Kenya.

Iceberg cooperates with local partners to ensure that the ICSs reach the target communities. The local partners are in charge of the distribution. They help Iceberg to gain access to the communities and identify local suppliers. Iceberg has provided enough training to the local partners to ensure that they can implement the project smoothly. The distribution has been on-site supervised by Iceberg. All data are collected by online system.

The crediting period of the project is expected to be 10 years. The average annual GHG emission reduction from the project is expected to be 222,137 tCO2e. The total GHG emission reduction is 2,221,373 tCO2e. This monitoring period is the first one, which is from 21/06/2022 to 20/06/2024. The GHG emission reduction of this monitoring period from the project is 94,407 tCO2e.

Audit History

| Audit type | Period | Program | Validation/verification body name | Number of years |
| --- | --- | --- | --- | --- |
| Validation/ verification | 21/06/2022—20/06/2024 | VCS | Validation/verification body name | Two years |

Sectoral Scope and Project Type

| Sectoral scope | 03 - Energy demand |
| --- | --- |
| Project activity type | II – Energy efficiency improvement projects |

Project Proponent

| Organization name | Guangzhou Iceberg Environmental Consulting Services Co., Ltd. |
| --- | --- |
| Contact person | Ji BAO |
| Title | General Manager |
| Address | No.106 Fengze East Road, Nansha District, Guangzhou, China |
| Telephone | +8613560420840 |
| Email | baoji@icebergchina.com; hanjin@icebergchina.com |

Other Entities Involved in the Project

No other entities involved. The Project proponent is the only entity which is in charge of the project.

Project Start Date

| Project start date | 21/06/2022 |
| --- | --- |
| Justification | The date of the first installation of the project ICS, which is the date on which the project began generating GHG emission reductions. |

Project Crediting Period

| Crediting period | ☐ Seven years, twice renewable ☒ Ten years, fixed ☐ Other (state the selected crediting period and justify how it conforms with the VCS Program requirements) |
| --- | --- |
| Start and end date of first or fixed crediting period | 21/06/2022 to 20/06/2032 |

Project Location

The project location is in the Republic of Kenya.

Table 1: Geographical coordinates of the Republic of Kenya

| Orientation | Latitude | Longitude |
| --- | --- | --- |
| Eastmost | 3°48′58″ N | 41°53′59″ E |
| Westmost | 1°03′35″ S | 33°55′46″ E |
| Southmost | 4°40′33″ S | 39°19′32″ E |
| Northmost | 4°15′41″ N | 35°23′57″ E |

Figure 1: Map of the Republic of Kenya

Title and Reference of Methodology

| Type (methodology, tool or module). | Reference ID, if applicable | Title | Version |
| --- | --- | --- | --- |
| Methodology | VMR0006 | VMR0006 Methodology for Installation of High Efficiency Firewood Cookstoves | 1.1 |
| Tool | 30 | TOOL30 Calculation of the fraction of non-renewable biomass | 3.0 |

Double Counting and Participation under Other GHG Programs

No Double Issuance

Is the project receiving or seeking credit for reductions and removals from a project activity under another GHG program?

☐   Yes			 ☒   No

Registration in Other GHG Programs

Is the project registered or seeking registration under any other GHG programs?

☐   Yes			 ☒   No

Double Claiming, Other Forms of Credit, and Scope 3 Emissions

No Double Claiming with Emissions Trading Programs or Binding Emission Limits

Are project reductions and removals or project activities also included in an emissions trading program or binding emission limit? See the VCS Program Definitions for definitions of emissions trading program and binding emission limit.

☐  Yes			☒  No

No Double Claiming with Other Forms of Environmental Credit

Has the project activity sought, received, or is planning to receive credit from another GHG-related environmental credit system? See the VCS Program Definitions for definition of GHG-related environmental credit system.

☐  Yes			☒  No

Supply Chain (Scope 3) Emissions

Do the project activities affect the emissions footprint of any product(s) (goods or services) that are part of a supply chain?

☒  Yes			☐  No

Is the project proponent(s) or authorized representative a buyer or seller of the product(s) (goods or services) that are part of a supply chain?

☒  Yes			☐  No

Has the project proponent(s) or authorized representative posted a public statement on their website saying, “Carbon credits may be issued through the Verified Carbon Standard project [project ID] for the greenhouse gas emission reductions or removals associated with [project proponent or authorized representative organization name(s)] [name of product(s) whose emissions footprint is changed by the project activities].”

☒  Yes			☐  No

The project proponent has posted a public statement on their website, the link of the website is: http://www.icebergchina.com/ensnew/contents/304/115.html .

Sustainable Development Contributions

Before the implementation of the project, local people in the project location used non-renewable biomass for cooking with open fire or three-stone fire. The project distributes fuel-efficient ICS to replace the baseline cookstoves in households, which leads to less firewood consumption, and reduces people’s exposure to hazardous indoor air. Hence people spend less time to collect firewood which reduces women and children’s drudgery. The production and distribution of ICSs have provided job opportunities to local people which will increase their incomes. And the project contributes to less deforestation and less GHG emissions too.

Table 1: Sustainable Development Contributions

| Row number | SDG target | SDG indicator | Net impact on SDG indicator | Current project contributions | Contributions over project lifetime |
| --- | --- | --- | --- | --- | --- |
| 1) | 1.4 | Project-specific indicator: Number of households with access to basic services | Implemented activities to increase | 26,130 households have received ICSs, and 25,966 are still operating. | Improved cookstove is a basic service necessary to lead a healthy and productive life, including saving time and money for wood fuel at the household level. The project proponent will distribute 100,000 ICSs to end users free, which will save their money on buying them. |
| 2) | 2.1 | 2.1.1 Prevalence of undernourishment. | Implemented activities to decrease | 26,130 households have received ICSs, and 25,966 are still operating, which help them improve their nutrition status. | Vulnerable populations often face significant risks to their health and nutrition due to inadequate access to the means of cooking their food, the project will improve food security and nutrition status for people in rural area of Kenya by reducing inadequate cooking due to fuel-saving cooking practices. |
| 3) | 3.9 | Project-specific indicator: Number of households experiencing health benefits due to reduced exposure to indoor air pollution | Implemented activities to decrease | By using ICS, all users admitted that the project cookstove had improved indoor air quality and reduced air quality related diseases, like cough or trachitis according to the monitoring survey. Thus, 25,966 households experiencing health benefits due to reduced exposure to indoor air pollution. | By using ICS, it will reduce people’s exposure to high PM2.5 and high CO due to higher efficiency of combustion leading to faster cooking and more complete combustion. |
| 4) | 4.3 | Project specific indicator: Number of persons who received any informal training | Implemented activities to increase | About 5 staff have received training about the survey method and monitoring plan etc. | The project proponent has provided and will provide vocational and relevant skills to local people non-formal education and training on issues related to climate change. The staff hired for the implementation of the project have been trained with skills in operations and surveying activities related to stove distribution and its monitoring under VCS. |
| 5) | 5.4 | 5.4.1 Proportion of time spent on unpaid domestic and care work, by sex, age, and location. | Implemented activities to decrease | The time spend on cooking and collecting firewood every day for women and girls who use ICSs has decreased about 27%. | The project will reduce women and children’s drudgery through time savings in reducing time spent on cutting, collecting, and carrying firewood from trees far away from households as well as cooking over toxic smoky open fires. |
| 6) | 6.6 | Project specific indicator: Quantity of non-renewable biomass in forest, which is a water-related ecosystem, saved by reducing fuel consumption | Implemented activities to increase | The project has saved 46,084.37 tonnes of non-renewable biomass during this monitoring period. | The project will save 108,435 tonnes of non-renewable biomass every year and it will result in a significant reduction of deforestation. Hence, it will protect the important water-related ecosystem. |
| 7) | 7.1 | 7.1.2 Proportion of population with primary reliance on clean fuels and technology. | Implemented activities to increase | 26,130 households have received ICSs, and 25,966 are still operating, which are primary reliance on clean fuels and technology. | The ICS distributed to Household is a cleaner cooking technology. The project will increase the proportion of population with primary reliance on clean fuels and technology in project area. |
| 8) | 8.3 8.5 | 8.3.1 Proportion of informal employment in total employment, by sector and sex. 8.5.1 Average hourly earnings of female and male employees, by occupation, age and persons with disabilities | Implemented activities to increase | 14 local people have been hired for the project, 18 of them are women. | The manufacturer will hire more people for the implementation of the project, such as productions, transporting and distribution of related devices. Iceberg and they will make sure that women, persons with disabilities, and minority will have equal chance to get the jobs. |
| 9) | 9.3 | 9.3.1 Proportion of small-scale industries in total industry value added | Implemented activities to increase | Prior to the Project, the production capacity of the factory is 10200 devices per month. After the implementation of the Project, the production capacity expanded to 16800 devices per month. | The local factories which produce ICS for the project are small-scale industries, which will expand production capacity to satisfy the needs. Thus, the upstream and downstream supply chain will benefit from the project. |
| 10) | 13.0 | Tonnes of greenhouse gas emissions avoided or removed | Implemented activities to increase | By saving 46,084.37 tonnes of non-renewable biomass, the project has prevented the release of 94,407 tonnes of CO2 emissions into the atmosphere. | The average annual GHG emission reduction from the project is expected to be 222,137 tCO2e due to less firewood combustion for cooking in the households. |
| 11) | 15.1 15.2 | 15.1.1 Forest area as a proportion of total land area 15.2.1 Progress towards sustainable forest management | Implemented activities to increase | The project has saved 46,084.37 tonnes of non-renewable biomass during this monitoring period. | The project will help local people consume less firewood as the ICS has higher thermal efficiency and it will result in a reduction of deforestation, which will protect forest. |

Commercially Sensitive Information

There is no commercially sensitive information has been excluded from the public version of the monitoring report.

Safeguards and Stakeholder Engagement

  - Stakeholder Engagement and Consultation

Stakeholder Identification

| Stakeholder Identification | The process used to identify stakeholders likely impacted by the project shows below: (a) Local people, communities and or representatives who are directly or indirectly affected by the project (b) Stakeholders with land-tenure rights within or adjacent to the project must be contacted (c) Local policy makers and representatives of local authorities (d) National government officials or National focal bodies responsible for the project in the host country (e) Local non-governmental organizations (NGOs), Women Groups working on topics relevant to the project or working with communities who are likely to be affected by the project Then the following stakeholders have been identified: (a) End-users of ICS (b) Cookstove manufacturer (c) Local NGOs (d) Local officials |
| --- | --- |
| Legal or customary tenure/access rights | The project only involves distributing ICS, there is no legal or customary tenure/access rights to territories and resources. |
| Stakeholder diversity and changes over time | The end uses are local people who receive ICS, mostly of them are women, because women cook in most households. The cookstove manufacturer produce and distribute the project ICS to the end users. The implementation of the project also needs the help from local NGOs and local officials. |
| Expected changes in well-being | Improved cookstove is a basic service necessary to lead a healthy and productive life, including saving time and money for wood fuel at the household level. The project proponent will distribute 100,000 ICSs, and the ICSs are produced in local factories. Hence the implementation of the project results in more job opportunities and higher income for local residents. Most of non-renewable biomass local people used for cooking is firewood, which generates high PM2.5 and high CO biomass smoke when incompletely burnt. By using ICS, it reduces people’s exposure to high PM2.5 and high CO due to higher efficiency of combustion leading to faster cooking and more complete combustion. It also reduces the burn risk, significant to children and toddlers due to enclosure of the fire in the combustion chamber. |
| Location of stakeholders | The end users who have received the project ICS during this monitoring period locates in the Kiambu County and Muranga County in the Republic of Kenya. Their information has been recorded in database. |
| Location of resources | The end users usually collect firewood near their villages. |

Stakeholder Consultation and Ongoing Communication

| Ongoing consultation | The project proponent has provided different measures to communicate and consult with stakeholders during this monitoring period: 1. Put a hard copy of opinion book in each village to record any incidences or occurrences. 2. A email address that could be used to complain any problems concerning the project. 3. Ensure that a close collaboration is groomed and maintained between the representatives of JCI and Iceberg with the users and the village elders. |  |
| --- | --- | --- |
| Date(s) of stakeholder consultation | 19/05/2022 |  |
| Communication of monitored results | The village leaders are in charge of reporting the problems stated in the opinion books to the representative of JCI, and the latter has checked the opinion books occasionally to see if there is problem, then they will report and find solutions with users. They have transferred opinions to Iceberg and JCI to make improvements. |  |
| Consultation records | There are 11 evaluation forms have been distributed and collected to survey the stakeholders’ opinions of the stakeholder consultation. |  |
| Stakeholder input |  | They all expressed their support to the project. During this monitoring period, the project also received their thanks and supports through the opinion book. |  |

Free, Prior, and Informed Consent

| Consent | The project proponent, end users and ICS manufacturer have signed ICS Donation and Carbon Transfer Agreements. The agreements have clarified each party’s duty and rights. There is no ongoing or unresolved conflicts and the project does not exacerbate nor influence the outcomes of unresolved conflicts. |
| --- | --- |
| Outcome of FPIC | The project only involves distributing ICS, the project has not encroached on land, relocated people without consent, and forced physical or economic displacement. |

Grievance Redress Procedure

| Grievances received | Resolution and outcome |
| --- | --- |
| No grievance received. | NA |

Public Comments

| Summary of comments received | Actions taken |
| --- | --- |
| No comment received. | NA |

Risks to Stakeholders and the Environment

|  | Risk identified | Mitigation or preventative measure taken |
| --- | --- | --- |
| Risks to stakeholder participation | No risk identified | The ICS is a basic service necessary to lead a healthy and productive life, including saving time and money for wood fuel at the household level. And the project ICS is distributed free and voluntarily participated by stakeholders. |
| Working conditions | No risk identified | The producing process is mature, there is no risk identified for working conditions. |
| Safety of women and girls | No risk identified | The project involves distributing ICS only, there is no risk identified for safety of women and girls. |
| Safety of minority and marginalized groups, including children | No risk identified | Any stakeholders can receive a ICS, despite their gender or religion. There is no risk identified for safety of minority or marginalized groups. |
| Pollutants (air, noise, discharges to water, generation of waste, release of hazardous materials) | No risk identified | The ICS can reduce the indoor air pollution via higher thermal efficiency. |

Respect for Human Rights and Equity

Labor and Work

| Discrimination and sexual harassment | There is no discrimination or sexual harassment has occurred during this monitoring period. |
| --- | --- |
| Management experience | There is no new entity involved in project design or implementation. |
| Gender equity in labor and work | The project ICSs are produced in local factory. After the implementation of the project, they have 12 full-time employees and 5 part-time employees, and 8 of them were women, 3 were with disabilities. And they are paid equally for equal work. |
| Human trafficking, forced labor, and child labor | The employees are working voluntarily, and have signed labor contracts with the factory. |

Human Rights

The project involves distributing ICS to local people free of charge only. ICS is a basic device in their life. And the project proponent has signed an agreement with the local people who voluntarily received an ICS. The project continues recognize, respect, and promote the protection of the rights of local community.

Indigenous Peoples and Cultural Heritage

The project involves distributing ICS to local people free of charge only. The staff of the project has been trained to preserve and protect cultural heritage during the implementation of the project. And during this monitoring period, they have not damaged the cultural heritage.

Property Rights

| Disputes over rights to territories and resources | N/A. |
| --- | --- |
| Respect for property rights | Comply with national laws and regulations. Obtain Free, Prior, and Informed Consent (FPIC) from affected communities. Recognize and secure community land rights. Respect customary rights and traditional land-use practices. Set up conflict resolution mechanisms. Build local capacity and empower communities. Implement robust monitoring and evaluation systems. Collaborate with local NGOs and indigenous rights groups. Maintain continuous engagement with affected communities. |

Benefit Sharing

| Summary of the benefit sharing plan | The project has no impact on property rights as described in Section 2.3.4 above. Not applicable. |
| --- | --- |
| Benefit sharing during the monitoring period | Not applicable. |

Ecosystem Health

|  | Risk identified | Mitigation or preventative measure taken during the monitoring period |
| --- | --- | --- |
| Impacts on biodiversity and ecosystems | No risk identified | The ICS has reduced the consumption of firewood, which protect the biodiversity and ecosystems. |
| Soil degradation and soil erosion | No risk identified | The project has no impact on soil degradation or soil erosion. |
| Water consumption and stress | No risk identified | The project has no impact on water consumption and stress. |
| Usage of fertilizers | No risk identified | The project has no impact on usage of fertilizers. |

Rare, Threatened, and Endangered species

The project is not located in, or adjacent to habitats for rare, threatened, or endangered species.

Introduction of species

N/A.

Ecosystem conversion

The project is not an ARR, ALM, WRC or ACoGS project, hence not applicable.

Implementation Status

Implementation Status of the Project Activity

The project has distributed 26,130 ICSs to end users free of charge during this monitoring period, which is from 21/06/2022 to 20/06/2024. Each ICS distributed in this project has a unique identification ID, the distribution date and the user’s basic information (e.g. name, address, phone number, unique identification ID) has been recorded in electronic database. The ICS is also labelled with programme’s logo. Hence, the above methods can make sure that it will avoid double counting of emission reductions. And the emissions reduction of this monitoring period can be calculated precisely based on above data.

From 21/06/2022 to 20/06/2024, there were 26,130 project ICSs were distributed, covering 50 villages, located in Kiambu County and Muranga County of Kenya.

Deviations

    - Methodology Deviations

There is no methodology deviation applied.

    - Project Description Deviations

There is no project description deviation applied during this monitoring period.

Grouped Projects

The project is not a grouped project.

Baseline Reassessment

Did the project undergo baseline reassessment during the monitoring period?

☐   Yes			 ☒   No

Data and Parameters

Data and Parameters Available at Validation

| Data / Parameter | fNRB,y |
| --- | --- |
| Data unit | Fraction of woody biomass saved by the project activity during year y that can be established as non-renewable biomass |
| Description | Calculated |
| Source of data | 0.89 |
| Value applied | Fraction of woody biomass saved by the project activity during year y that can be established as non-renewable biomass |
| Justification of choice of data or description of measurement methods and procedures applied | As per the “TOOL30: Calculation of the fraction of non-renewable biomass, version 3.0”. Variable; Unit; Value. Total woody biomass consumption (H); t/yr; 27,734,283. Renewable biomass (RB); t/yr; 3,050,976. Non-renewable biomass (NRB); t/yr; 24,683,307. fNRB; -; 0.89. |
| Purpose of data | Calculation of emission reductions |
| Comments | . |

| Data / Parameter | NCVwood fuel |
| --- | --- |
| Data unit | TJ/tonne |
| Description | Net calorific value of the non-renewable woody biomass that is substituted or reduced |
| Source of data | 2006 IPCC Guidelines for National Greenhouse Gas Inventories; Volume 2 Energy, Chapter 1 Introduction: Table 1.2 Default net calorific values (NCVs) and lower and upper limits of the 95 percent confidence intervals. |
| Value applied | 0.0156 |
| Justification of choice of data or description of measurement methods and procedures applied | 2006 IPCC default value as no update in 2019 IPCC refinement |
| Purpose of data | Calculation of emission reductions |
| Comments | - |

| Data / Parameter | EFwf, CO2 |
| --- | --- |
| Data unit | tCO2 /TJ |
| Description | CO2 emission factor for the use of wood fuel in baseline scenario |
| Source of data | 2006 IPCC Guidelines for National Greenhouse Gas Inventories; Volume 2 Energy, Chapter 2 Stationary Combustion: Table 2.5 Default emission factors for stationary combustion in the residential and agriculture/forestry/fishing/fishing farms categories. |
| Value applied | 112 |
| Justification of choice of data or description of measurement methods and procedures applied | 2006 IPCC default value as no update in 2019 IPCC refinement |
| Purpose of data | Calculation of emission reductions |
| Comments | - |

| Data / Parameter | EFwf,non CO2 |
| --- | --- |
| Data unit | tCO2 /TJ |
| Description | Non-CO2 emission factor for the use of wood fuel in baseline scenario |
| Source of data | 2006 IPCC Guidelines for National Greenhouse Gas Inventories; Volume 2 Energy, Chapter 2 Stationary Combustion |
| Value applied | 26.23 |
| Justification of choice of data or description of measurement methods and procedures applied | 2006 IPCC default value as no update in 2019 IPCC refinement |
| Purpose of data | Calculation of emission reductions |
| Comments | - |

| Data / Parameter | ηp |
| --- | --- |
| Data unit | Fraction |
| Description | Efficiency of project stove at the start of project activity. |
| Source of data | Manufacturer’s specification and Test Report by KIRDI Stove Testing Centre in Kenya using WBT test protocol 4.2.3 |
| Value applied | 27.2% |
| Justification of choice of data or description of measurement methods and procedures applied | This parameter shall be determined ex-ante |
| Purpose of data | Calculation of emission reductions |
| Comments | - |

Data and Parameters Monitored

| Data / Parameter | Ny,i,j |
| --- | --- |
| Data unit | Number |
| Description | Number of project devices of type i and batch j operating during year y |
| Source of data | Monitoring Survey |
| Description of measurement methods and procedures to be applied | The total distribution data has been recorded. Then the number of devices still operating was obtained by multiplying the total number and usage rate. The usage rate survey was included in the Monitoring Survey. Multi-stage sampling was applied in the Monitoring Survey during this monitoring period. 8 villages were randomly chosen in the first stage of the sampling process. Then 20 households were randomly chosen from each of the 8 villages. |
| Frequency of monitoring/recording | At least once every two years |
| Value monitored | 25,966 is applied for this monitoring period. |
| Monitoring equipment | 26,130 project ICSs have been distributed, and according to monitoring survey conducted by local partners from 01/09/2023 to 14/11/2023, the usage rate is 99.38%. Hence, Ny,i,j=26,130*99.38%=25,966 |
| QA/QC procedures to be applied | The staff has been trained to conduct the data recording and survey. |
| Purpose of the data | Calculation of emission reductions |
| Calculation method | Proportion of operational stoves obtained from the survey is multiplied by the total commissioned stoves to arrive at this value. |
| Comments | NA |

| Data / Parameter | ηnew,y,i,j |
| --- | --- |
| Data unit | Fraction |
| Description | Efficiency of the improved cookstove type i and batch j implemented as part of the project activity |
| Source of data | Calculation |
| Description of measurement methods and procedures to be applied | The total distribution data has been recorded. Then the number of devices still operating was obtained by multiplying the total number and usage rate. The usage rate survey was included in the Monitoring Survey. Multi-stage sampling was applied in the Monitoring Survey during this monitoring period. 8 villages were randomly chosen in the first stage of the sampling process. Then 20 households were randomly chosen from each of the 8 villages. |
| Frequency of monitoring/recording | The PP uses equation 5 of the applied methodology VMR0006 version 1.1 to calculate the efficiency, and therefore this parameter does not need to be monitored. |
| Value monitored | Age(y); ηnwe,y,i,j. 1; 25.57%. 2; 25.31%. |
| Monitoring equipment | NA |
| QA/QC procedures to be applied | NA |
| Purpose of the data | Calculation of emission reductions |
| Calculation method | Efficiency of the improved cookstoves is estimated using equation 5 of the applied methodology where loss in efficiency per year is calculated, and therefore this parameter does not need to be monitored. |
| Comments | NA |

| Data / Parameter | By=1,new,i,j,survey |
| --- | --- |
| Data unit | tonnes |
| Description | Quantity of woody biomass used by project devices in tonnes per device of type i |
| Source of data | Fuel Consumption Survey |
| Description of measurement methods and procedures to be applied | The quantity of woody biomass used by project devices per device per day has been surveyed by Fuel Consumption Survey. The Fuel Consumption Survey was included in the Monitoring Survey. Multi-stage sampling was applied in the Monitoring Survey during this monitoring period. 8 villages were randomly chosen in the first stage of the sampling process. Then 20 households were randomly chosen from each of the 8 villages. The sampled households have recorded their daily fuel consumption in seven consecutive days. Then the average quantity of woody biomass used by project devices was calculated. |
| Frequency of monitoring/recording | Determined in the first year of project implementation |
| Value monitored | 0.5452kg/person/day according to the result of the fuel consumption survey. And the average number of persons in household is 4.18 according to the ICS distribution statistic form. Therefore, the quantity of woody biomass used by project devices in tonnes per device per year is 0.83 tonnes/device/year (0.5452*4.18*365/1000=0.83). |
| Monitoring equipment | Fuel Consumption Survey, and the result was recorded in Grid F176 of the submitted spreadsheet “2_Data recording of Monitoring Survey”, which used to calculate this parameter in Grid B15 of the submitted spreadsheet “1_MR-ER calculation sheet”. |
| QA/QC procedures to be applied | NA |
| Purpose of the data | Calculation of emission reductions |
| Calculation method | NA |
| Comments | NA |

| Data / Parameter | ηold |
| --- | --- |
| Data unit | Fraction |
| Description | Efficiency of baseline cookstove |
| Source of data | - Default value: 0.1 or 0.2; or - Surveyed prior to implementation of project activity The baseline survey was conducted by local staff of the project proponent in Kenya. It was taken from 25/05/2022 to 06/06/2022 among 120 households from 6 villages. |
| Description of measurement methods and procedures to be applied | (a) A default value of 0.1 shall be used if baseline device is a three-stone fire using firewood (not charcoal), or a conventional device with no improved combustion air supply or flue gas ventilation, that is without a grate or a chimney. (b) A default value of 0.2 shall be used for other types of devices. (c) If more than one type of baseline device is being replaced in the project region, weighted average values (taking the amount of woody biomass consumed by each device as the weighting factor) shall be used. (d) If this parameter is surveyed, project promoters may use simplified guidelines stated under Option (b) in Section 8.4 above for arriving at the minimum sample size. The following is outcome of baseline survey: Kind of cook stove in baseline scenario; Number of households; Percentage. open fire; 4; 3.33%. three-stone fire; 116; 96.67%. conventional stove without grate or chimney; 0; 0.00%. LPG stove; 0; 0.00%. basic charcoal or coal cookstove; 0; 0.00%. improved stove with grate or chimney; 0; 0.00%. portable improved cookstove; 0; 0.00%. others; 0; 0.00%. Total; 120; 100.00%. The result of baseline survey is 3.33% using open fire and 96.67% three-stone fire, which 100% of them belongs to option(a) above. Hence, the applied value is 0.1 of η_old. |
| Frequency of monitoring/recording | Fixed for each individual household at the time of project implementation |
| Value monitored | 0.1 is applied based on baseline survey |
| Monitoring equipment | NA |
| QA/QC procedures to be applied | NA |
| Purpose of the data | Calculation of emission reductions |
| Calculation method | NA |
| Comments | NA |

| Data / Parameter | Life span |
| --- | --- |
| Data unit | Years |
| Description | Project promoters to state the operating lifetime of project device for projects opting Equation 5 for determining project stove efficiency. |
| Source of data | Manufacturer’s specification |
| Description of measurement methods and procedures to be applied | NA |
| Frequency of monitoring/recording | Once at the time of project stove installation |
| Value monitored | 7 |
| Monitoring equipment | NA |
| QA/QC procedures to be applied | NA |
| Purpose of the data | Calculation of emission reductions |
| Calculation method | NA |
| Comments | NA |

Monitoring Plan

The local partner of Iceberg (i.e. project proponent) is in charge of the implementation of the monitoring plan and reporting to Iceberg. Iceberg is in charge of designing the monitoring plan and completing the monitoring report. The local staff has been trained on measuring, recording, storing, aggregating, collating and reporting the data to make sure they can monitor the project in line with the requirements.

Sampling survey has been applied for this monitoring period.

（a）Sampling Plan

As per the Standard for Sampling and Surveys for CDM Project Activities and Programmes of Activities, Version 09.0:

Sampling design

(1) Objectives and reliability requirements

The objective is determining the value of parameter Ny,i,j and By=1,new,i, survey during the monitoring period, and with a 90/10 confidence/precision compliance with the applied methodology.

The following parameters may be determined by sampling:

| Parameter | Description | Frequency |
| --- | --- | --- |
| Ny,i,j | Number of project devices of type i and batch j operating during year y | Biennial |
| By=1,new,i,survey | Quantity of woody biomass used by project devices in tonnes per device of type i and batch j | Determined in the first year of project implementation |

(2) Target population

The target population are the households who have received the project ICSs.

(3) Sampling method and size

Multi-stage sampling was applied in the sampling survey during this monitoring period. 8 villages were randomly chosen in the first stage of the sampling process. Then 20 households were randomly chosen from each of the 8 villages. The equation 16 and 33 of “Guideline for Sampling and surveys for CDM project activities and programmes of activities” (version 04.0) were used to determine the above sample size:

Where:

| C | = | Number of villages that should be sampled |
| --- | --- | --- |
| M | = | Total number of villages in the population |
| u | = | Number of households to be sampled within each village |
| N | = | Average households per village |
| SDB2 | = | variance between villages |
| SDW2 | = | average within village variation |
| p | = | Overall proportion |
| 1.645 | = | Represents the 90% confidence required |
| 0.1 | = | Represents the 10% relative precision |

Where:

| M | = | Total number of villages in the population |
| --- | --- | --- |
| N | = | Average households per village |
| u | = | Number of households that have been pre-specified to be sampled per village |
| 1.645 | = | Represents the 90% confidence required |
| 0.1 | = | Represents the 10% relative precision |

To achieve 90/10 confidence/precision, for By=1,new,i,survey, the minimum number of the sampled villages is 6; for Ny,i,j, the minimum number of the sampled villages is 1. As the project proponent and its local partner has surveyed 8 villages, the survey met the required 90/10 confidence/precision.

The Fuel Consumption Survey was conducted by local staff from 03/05/2023 to 06/06/2023, and the Project Survey, which including Usage Survey was conducted from 01/09/2023 to 14/11/2023. Please refer to the submitted spreadsheet “2_Data recording of Monitoring Survey” for details.

(b) Data has been collected

Besides the above parameters, the following data has been collected as per the applied methodology:

- Date of distribution

- Geographic location of the household who received the ICS

- Quantity of project ICSs distributed

- Name and telephone number, and address of received households

- unique identification ID for each ICS that is distributed

- Whether the cookstoves distributed under the project are being used

- Whether baseline stoves or other stoves are being used along with project stoves

The information collected will be stored in the electronic database for 2 years after the end of crediting period.

Quality assurance/Quality control

Training about monitoring plan has been provided to local staff of project proponent’s local partner, including survey protocol, method of data recording and analysis. The monitoring plan has been carried out by qualified personnel trained for quality assurance and quality control. The project proponent inspects local partner to confirm that the personnel are qualified and the monitoring plan has been properly implemented. The data collected has been cross checked by the project proponent.

The organizational structure for monitoring is shown as the bellow:

Local partner

Project proponent

cooperate

cross check data

design                                                               implement

Monitoring plan

(c) Implementation plan

The scope and objectives of the internal audit, including the processes or departments have been clearly defined. Then we developed an audit plan outlining the audit schedule, resources required, audit criteria, and responsibilities of audit team member. The main survey methods applied in the sampling plan include hardcopy questionnaires, online questionnaires, and face to face interview. The potential of refusals and other means of non-responses has been taken into account.

The audit team should classify and document non-conformities identified during the audit process, categorizing them based on severity and impact on quality, safety, or compliance. If they are in accordance with the applied methodology and other related rules, a change may be conducted in the validated monitoring plan. Otherwise, revision and improvement will be conducted in the monitoring. The related ERs will not be claimed in the monitoring report until the non-conformance has been corrected in the latter case.

Quantification of GHG Emission Reductions and Removals

Baseline Emissions

The applied methodology does not account for baseline emissions separately, but instead quantifies emission reductions as a function of the reduction in the amount of non-renewable biomass fuel consumption in the efficient project stoves as compared to baseline stoves. Please refer to Section 5.4 of the MR.

Project Emissions

The applied methodology does not account for project emissions separately, but instead quantifies emission reductions as a function of the reduction in the amount of non- renewable biomass fuel consumption in the efficient project stoves as compared to baseline stoves. Please refer to Section 5.4 of the MR.

Leakage Emissions

Leakage is considered as default 0.95 in accordance with the applied methodology.

GHG Emission Reductions and Carbon Dioxide Removals

The project activity replaces traditional wood-based stove with ICS, therefore net GHG emission reductions are calculated by applying Equations 1 and 2.

ERy=ijERy,i,j                                                                                                      Equation (1)

Where:

| i | = | Indices for the situation where more than one type/model of improved cook stove is introduced to replace three-stone fire |
| --- | --- | --- |
| j | = | Indices for the situation where there is more than one batch of improved cook stove of type i |
| ERy | = | Emission reductions during year y in t CO2e |
| ERy,i,j | = | Emission reductions by improved cook stove of type i and batch j during year y in t CO2e |

ERy,i,j=By,saving,i,j×fNRB,y×NCVwood fuel×EFwf,CO2+EFwf,non CO2×Ny,i,j×0.95    Equation (2)

Where:

| By,saving,i,j | = | Quantity of woody biomass that is saved in tonnes per improved cook stove of type i and batch j during year y |
| --- | --- | --- |
| fNRB,y | = | Fraction of woody biomass that can be established as non-renewable biomass (fNRB). The value is calculated to be 0.89. |
| NCVwood fuel | = | Net calorific value of the non-renewable woody biomass that is substituted or reduced (IPCC default for wood fuel, 0.0156 TJ/tonne) |
| EFwf, CO2 | = | CO2 emission factor for the use of wood fuel in baseline scenario (IPCC default for wood fuel, 112 tCO2/TJ) |
| EFwf,non CO2 | = | Non-CO2 emission factor for the use of wood fuel in baseline scenario (IPCC default for wood fuel, 26.23 tCO2/TJ) |
| Ny,i,j | = | Number of improved cook stoves of type i and batch j operating during year y |
| 0.95 | = | Discount factor to account for leakage |

The quantity of woody biomass saved due to implementation of improved cook stoves is estimated by Equations 4 of the applied methodology:

By,savings,i,j=By=1,new,i,survey×ηnew,y,i,jηold-1                                                              Equation (4)

Where:

| ηold | = | Efficiency of baseline cookstove. The value is 0.1 based on baseline survey. |
| --- | --- | --- |
| ηnew,y,i,j | = | Efficiency of the improved cook stove type i and batch j determined using Equation 5. |
| By=1,new,i,survey | = | Annual quantity of woody biomass used by improved cook stoves in tonnes per device of type i and batch j, determined in the first year of the implementation of the project through a sample survey. |

ηnew,y,i,j=ηp×DFny-1×0.94                                                                                    Equation (5)

Where:

| ηp | = | Efficiency of project stove (fraction) at the start of project activity; the value is 27.2% as per the specifications provided by manufacturer |
| --- | --- | --- |
| DFny-1 | = | Discount factor to account for efficiency loss of project cookstove per year of operation (fraction). This value may be based on actual monitoring or based on manufacturer’s declaration on expected loss in efficiency or through publicly available literature on relevant industry standards. Alternatively default value of 0.99 efficiency loss per year can be considered. |
| 0.94 | = | Adjustment factor to account for uncertainty related to project cookstove efficiency test |

As validated in the registered PD, the values of relative parameters below have been applied.

ηp=27.2%;

DFn=0.99;

Therefore, ηnew,y,i,j is calculated as below:

| Age(y) | ηnew,y,i,j |
| --- | --- |
| 1 | 25.57% |
| 2 | 25.31% |

The project has distributed 26,130 ICSs to households during the monitoring period. According to the survey, there is only one household not use project ICS among the 160 sampled households. Therefore, the annual loss rate is 1/160. The usage rate is 159/160=99.38%.

Therefore, the Ny,i,j is applied as below:

26,130 project ICSs have been distributed during this monitoring period, hence,

Ny,i,j=26,130*99.38%=25,966

By=1,new,i,survey=0.83 tonnes/device/year according to monitoring survey.

GHG emission reductions of the monitoring period is shown below:

| Vintage period | Baseline emissions (tCO2e) | Project emissions (tCO2e) | Leakage emissions (tCO2e) | Reduction VCUs (tCO2e) | Removal VCUs (tCO2e) | Total VCUs (tCO2e) |
| --- | --- | --- | --- | --- | --- | --- |
| 21/06/2022-31/12/2022 | N.A. | N.A. | A discount factor of 0.95 is applied for leakage | 18,120 | 0 | 18,120 |
| 01/01/2023-31/12/2023 | N.A. | N.A. | A discount factor of 0.95 is applied for leakage | 48,030 | 0 | 48,030 |
| 01/01/2024-20/06/2024 | N.A. | N.A. | A discount factor of 0.95 is applied for leakage | 28,257 | 0 | 28,257 |
| Total | N.A. | N.A. | A discount factor of 0.95 is applied for leakage | 94,407 | 0 | 94,407 |

Compare the estimated ex-ante GHG emission reductions and removals and the achieved emission reductions and removals for this monitoring period:

| Vintage period | Ex-ante estimated reductions/ removals | Achieved reductions/ removals | Percent difference | Explanation for the difference |
| --- | --- | --- | --- | --- |
| 21/06/2022-31/12/2022 | 23,340 | 18,120 | 22.36% | There are three main reasons: 1. Due to a lack of funds, only 26,130 ICSs have been distributed during this monitoring period, which is the first two years of the project, and the project proponent planned to distribute 100,000 ICSs as described in registered PDD. The actual distribution quantity only counts about a quarter of the planned distribution quantity. 2. For ex-ante emission reduction calculation, it was assumed that 1.16tonnes/device/year. But the value applied in this monitoring period is only 0.83tonnes/device/year according to the survey, which is 28.27% less than the former. 3. The average operation days of all devices during the first year of this monitoring period is 202.92, which only accounts 55.59% of one whole year. |
| 01/01/2023-31/12/2023 | 160,369 | 48,030 | 70.05% |  |
| 01/01/2024-20/06/2024 | 128,145 | 28,257 | 77.95% |  |
| Total | 311,854 | 94,407 |  |  |

- APPENDIX 1: Statement about outcomes of SDGs

Statement from Jambo Capital Initiative which is the project implementer of the project.

Projects, activities, or methodologies may be developed under any of the 16 VCS sectoral scopes: https://verra.org/programs/verified-carbon-standard/vcs-program-details/#sectoral-scopes

https://www.fao.org/3/I9967EN/i9967en.pdf

Compared between baseline survey and monitoring survey, the result is calculated in Grid AV165 and AZ165 of the submitted spreadsheet “2_Data recording of Monitoring Survey”.

The result is recorded in Grid B25 of the submitted document “1_MR-ER calculate sheet”.

Please refer to appendix 1 “Statement about outcomes of SDGs”

Please refer to appendix 1 “Statement about outcomes of SDGs”.

AMS II.G. Version 11

2006 IPCC Guidelines for National Greenhouse Gas Inventories; Chapter 2 Stationary Combustion

2006 IPCC Guidelines for National Greenhouse Gas Inventories; Chapter 2 Stationary Combustion